## Inputs Project
Holger Stieb (PJM) - 28-08-2024
Initial draft Release Plan (B.Renon in meeting with D.Schultte/H.Stieb) - May 2024

## PBS+Estim
Assumptions
1 | PMIC and GDU references frozen
2 | PMIC and GDU same on both path
3 | Light / minimal process sufficient (no DOORS requirements and test spec) for this PreDev
4 | HPM does not offer close loop management for the Motor Control
5 | MPS technology is SPI based
6 | HW available for SW development 4 months before expected delivery (1xHEF / 1xHRO)
7 | "20ms pulse" = special UC for PMIC
8 | Heartbeat nice to have
Team Allocation until Q1.2025 (at least)
HEF - Mael Languil | 50%
HEF - Nasser Belmkadem | 50%
HRO - Simona Spataru | 75%
HEF - Benoit Renon | 5%
Total FTE | 1.8
|  | Workload (days) | Workload (hours) | HEF contrib | HEF hours | HRO contrib | HRO hours |  | CW43 | CW44 | CW45 | CW46 | CW47 | CW48 | CW49 | CW50 | CW51 | CW52 | CW53 | CW54
General activities (release, support, meetings, …) |  | 29 | 232 |  | 158 |  | 74 | 232
| Meetings / project alignments | 5 | 40 | 2 | 26 | 1 | 14
| Overall integration & release | 5 | 40 | 1 | 40 |  | 0 | bar: CW47; CW51; CW53
| Documentation : UsM, Release Note | 5 | 40 | 1.5 | 30 | 0.5 | 10
| Documentation : minimal test plan / report | 5 | 40 | 1 | 20 | 1 | 20
| HW setup | 4 | 32 | 1 | 16 | 1 | 16
| Rollout & TestLab support | 5 | 40 | 2 | 26 | 1 | 14
GDU development (embedded drivers + test GUI) |  | 36 | 288 |  | 288 |  | 0 | 288
| Collection of project UC & datasheet analysis | 5 | 40 | 1 | 40 |  | 0
| HPM embedded - Implementation GDU driver V1 (init SPI, ports, basic config, switch to normal mode,) | 10 | 80 | 1 | 80 |  | 0
| HPM embedded - Implementation GDU driver V2 (bug fix + read/write registers + extended functions ) | 5 | 40 | 1 | 40 |  | 0
| HPM embedded - Integration | 4 | 32 | 1 | 32 |  | 0
| HPM GUI - Design interface for GDU | 5 | 40 | 1 | 40 |  | 0
| Overall feature test (plan + exec + report) | 5 | 40 | 1 | 40 |  | 0
| Documentation: UsM feature | 2 | 16 | 1 | 16 |  | 0
PMIC development (embedded drivers + test GUI) |  | 52 | 416 |  | 106 |  | 310 | 416
| Collection of project UC & datasheet analysis | 5 | 40 | 1 | 20 | 1 | 20
| HPM embedded - Implementation PMIC driver V1 (init SPI, ports, basic config, switch to normal mode,) | 10 | 80 |  | 0 | 1 | 80
| HPM embedded - Implementation PMIC driver V2 (bug fix + read/write registers + extended functions) | 10 | 80 |  | 0 | 1 | 80
| HPM embedded - Integration | 5 | 40 | 1 | 20 | 1 | 20
| HPM GUI - Design interface for PMIC | 10 | 80 | 1 | 40 | 1 | 40
| Overall feature test (plan + exec + report) | 10 | 80 | 0.5 | 26 | 1 | 54
| Documentation: UsM feature | 2 | 16 |  | 0 | 1 | 16
PWM generation & Current acquisition on Powerstage (MOSFET) development (embedded drivers + test GUI) |  | 25 | 200 |  | 104 |  | 96 | 200
| Collection of project UC & datasheet analysis | 2 | 16 | 1 | 8 | 1 | 8
| HPM embedded - Implementation PWM driver | 5 | 40 | 1 | 20 | 1 | 20
| HPM embedded - Implementation ADC driver for currents | 5 | 40 |  | 0 | 1 | 40
| HPM embedded - Implementation of synchronized PWM & ADC acq | 4 | 32 | 1 | 32 |  | 0
| HPM embedded - Integration | 2 | 16 | 1 | 8 | 1 | 8
| HPM GUI - Design interface for PWM & Current Acquisition | 3 | 24 | 1 | 24 |  | 0
| Overall feature test (plan + exec + report) | 3 | 24 | 0.5 | 8 | 1 | 16
| Documentation: UsM feature | 1 | 8 | 1 | 4 | 1 | 4
MPS development (embedded drivers + test GUI) |  | 22 | 176 |  | 16 |  | 160 | 176
| Collection of project UC & datasheet analysis | 1 | 8 | 0.5 | 2 | 1 | 6
| HPM embedded - Implementation MPS driver V1 (init SPI, ports, basic config, switch to normal mode,) | 8 | 64 |  | 0 | 1 | 64
| HPM embedded - Implementation MPS driver V2 (bug fix + read/write registers + extended functions ) | 3 | 24 |  | 0 | 1 | 24
| HPM embedded - Integration | 1 | 8 | 1 | 4 | 1 | 4
| HPM GUI - Design interface for MPS | 4 | 32 | 0.5 | 10 | 1 | 22
| Overall feature test (plan + exec + report) | 3 | 24 |  | 0 | 1 | 24
| Documentation: UsM feature | 2 | 16 |  | 0 | 1 | 16
Internal COM development (embedded drivers + test GUI) |  | 6 | 48 |  | 48 |  | 0 | 48
| Collection of project UC & datasheet analysis | 1 | 8 | 1 | 8 |  | 0
| HPM embedded - Integration / take-over PPE CAN drivers | 1 | 8 | 1 | 8 |  | 0
| HPM GUI - Design interface for IEC | 1 | 8 | 1 | 8 |  | 0
| Overall feature test (plan + exec + report) | 2 | 16 | 1 | 16 |  | 0
| Documentation: UsM feature | 1 | 8 | 1 | 8 |  | 0
Heartbeat development (embedded drivers) |  | 5 | 40 |  | 40 |  | 0 | 40
| Collection of project UC & datasheet analysis | 1 | 8 | 1 | 8 |  | 0
| HPM embedded - Integration / take-over PPE timer & DIO | 1 | 8 | 1 | 8 |  | 0
| Overall feature test (plan + exec + report) | 2 | 16 | 1 | 16 |  | 0
| Documentation: UsM feature | 1 | 8 | 1 | 8 |  | 0
[5 empty] | Total HEF |  | Total HRO | Total
|  |  |  | Hours: | 760 |  | 640 | 1400
|  |  |  | CWeeks: | 19 |  | 22
[5 empty] | 42180 |  | 30720 | 72900
Summary:
~760 hours HEF => ~4 months given our allocation + vacations
~640 hours HRO => ~4 months given our allocation + vacations
~1400 hours total
See assumptions

## Sheet1 (hidden)
| HEF hours | HRO hours
General activities (release, support, meetings, …) | 158 | 74
GDU development (embedded drivers + test GUI) | 288 | 0
PMIC development (embedded drivers + test GUI) | 106 | 310
PWM generation & Current acquisition on Powerstage (MOSFET) development (embedded drivers + test GUI) | 104 | 96
MPS development (embedded drivers + test GUI) | 16 | 160
Internal COM development (embedded drivers + test GUI) | 48 | 0
Heartbeat development (embedded drivers) | 40 | 0
| 760 | 640

## ReleasePlan
Release | v0.1 | V0.2 | V0.3 | V0.4 | V1.0 | V1.1 | V1.2
Date | 2024-10-18 | 2024-11-08 | 2024-11-29 | 20-dec-24 | 2024-01-10 | 2024-01-31 | 2024-02-21
Feature
GDU (DRV3233) | M1 | M2 | M2 | M3 | M3 | M4 | M4
PMIC (TPS653861) | M1 | M2 | M2 | M3 | M3 | M4 | M4
PWM generation & Current acquisition on Powerstage (MOSFET) |  | M1 | M2 | M2 | M3 | M3 | M4
MPS (DS A33020) |  | M1 | M2 | M2 | M3 | M3 | M4
Internal COM |  |  | M1 | M2 | M2 | M3 | M4
Heartbeat |  |  | M1 | M2 | M3 | M4 | M4
|  |  | A0 |  | P0 ?
*Cadence = one release every 3 weeks
Maturity Level
Embedded draft functional and basic documentation | bar: v0.1 to V0.2
Linked (embedded & HMI) feature functionnal and ready for manual test | v0.1: M2; V0.3: Human Machine Interface = HMI
Full functional feature ready for official test campaign | bar: v0.1 to V0.2
Full documentation and UserManual | bar: v0.1 to V0.2
Milestones
First Sample (A0) = | v0.1: Early December (CW 48)
First Production Release (P0) = | v0.1: Early January ?

## Planning
|  | CW42 | CW43 | CW44 | CW45 | CW46 | CW47 | CW48 | CW49 | CW50 | CW51 | CW52 | CW01 | CW02 | CW03 | CW04 | CW05 | CW06 | CW07
| Milestones | CW42: V0.1; CW45: V0.2; CW48: V0.3; CW51: V0.4; CW02: V1.0; CW05: V1.1
Dates | bar: CW45; CW02
General activities (release, support, meetings, …)
| Meetings / project alignments | X | X | X | X | X | X | X | X | X | X | Vacation |  | X | X | X | X
Overall integration & release | bar: CW45; CW48; CW51; CW02; CW05
Documentation : UsM, Release Note | bar: CW02
Documentation : minimal test plan / report
HW setup
Rollout & TestLab support
GDU development (embedded drivers + test GUI)
| Collection of project UC & datasheet analysis | CW42: Done
| HPM embedded - Implementation GDU driver V1 (init SPI, ports, basic config, switch to normal mode,) | CW42: Done
| HPM embedded - Implementation GDU driver V2 (bug fix + read/write registers + extended functions ) | CW43: X; CW44: X; CW45: X; CW46: X; CW47: Done
| HPM embedded - Basic documentation | CW43: Done
| HPM embedded - Integration | CW46: Done
| HPM GUI - Design interface for GDU | CW44: X; CW45: X; CW47: X; CW48: Done
Overall feature test (plan + exec + report) | bar: CW49 to CW51
Documentation: UsM feature
PMIC development (embedded drivers + test GUI)
| Collection of project UC & datasheet analysis | CW42: Done
| HPM embedded - Implementation PMIC driver V1 (init SPI, ports, basic config, switch to normal mode,) | CW42: Done
| HPM embedded - Implementation PMIC driver V2 (bug fix + read/write registers + extended functions) | CW43: X; CW44: X; CW45: Done
| HPM embedded - Basic documentation | CW45: Done
| HPM embedded - Integration | CW45: Done
| HPM GUI - Design interface for PMIC | CW47: X; CW48: Done
Overall feature test (plan + exec + report) | bar: CW49 to CW51; CW02
Documentation: UsM feature
PWM generation & Current acquisition on Powerstage (MOSFET) development (embedded drivers + test GUI)
Collection of project UC & datasheet analysis | bar: CW43
| HPM embedded - Implementation PWM driver | CW43: X; CW44: X; CW46: Done
| HPM embedded - Implementation ADC driver for currents | CW44: X; CW45: X; CW46: Done
| HPM embedded - Implementation of synchronized PWM & ADC acq | CW45: X; CW46: Done
| HPM embedded - Integration | CW46: Done
| HPM GUI - Design interface for PWM & Current Acquisition | CW47: X; CW48: Done
Overall feature test (plan + exec + report) | bar: CW02 to CW03
Documentation: UsM feature
MPS development (embedded drivers + test GUI)
| Collection of project UC & datasheet analysis | CW43: X; CW44: Done
| HPM embedded - Implementation MPS driver V1 (init SPI, ports, basic config, switch to normal mode,) | CW43: X; CW44: X; CW45: Done
| HPM embedded - Implementation MPS driver V2 (bug fix + read/write registers + extended functions ) | CW46: Done
| HPM embedded - Integration | CW45: X; CW46: Done
| HPM GUI - Design interface for MPS | CW48: X; CW49: Done
Overall feature test (plan + exec + report) | bar: CW02 to CW03
Documentation: UsM feature
Internal COM development (embedded drivers + test GUI)
Collection of project UC & datasheet analysis | bar: CW43
| HPM embedded - Development of UART driver | CW43: X; CW44: X; CW45: X; CW49: X; CW50: X; CW51: X; CW52: X; CW01: Done
HPM embedded - Implementation of UART and SPI for IEC | bar: CW02 to CW05
HPM embedded - Integration | bar: CW05
HPM GUI - Design interface for IEC
Overall feature test (plan + exec + report)
Documentation: UsM feature
Heartbeat development (embedded drivers)
Collection of project UC & datasheet analysis | bar: CW05
HPM embedded - Integration / take-over PPE timer & DIO | bar: CW05
Overall feature test (plan + exec + report) | bar: CW05
Documentation: UsM feature
Color Code
Nasser BELMKADEM | bar: CW42
Simona Camelia SPATARU | bar: CW42
Mael LANGUIL | bar: CW42
Everyone | bar: CW42